## Summary
NEVO TOWER - EXECUTIVE SUMMARY
Generated: 2025-11-06 03:56
TOTAL DEVELOPMENT COST
SC Cash Payment (Project Cost)
Hard Costs
Soft Costs
TOTAL PROJECT COST | 100.0%
REVENUE
Total Revenue
PROFITABILITY
Gross Profit
Profit Margin
Return on Cost (ROI)
Cost per Unit (50 Condos) |  | Excluding synagogue cost
Cost per NSF
Revenue per NSF

## Assumptions
NEVO TOWER - PROJECT ASSUMPTIONS
PROJECT INFORMATION
Total GSF | 108675 | 100%
Total NSF | 86940
Residential Units | 50 | 100%
LAND PARTNER STRUCTURE
Land Partner - Land (In-Kind) | 8000000 |  | Land value $10M total - $2M paid cash
SC Key Money (Month 0) | 1250000 |  | Developer pays SC to enter deal
SC Payment (Month 6) | 750000 |  | Additional payment to SC
Land Partner - Deferred Payment | 0 | 0% | $8M paid at exit (NOT a cost)
COST ASSUMPTIONS
GC Overhead & Profit | 10% | %
General Conditions | 9% | %
Design Contingency | 8% | %
Construction Contingency | 5% | %
Owner Contingency | 3% | %
A&E Fee Rate | 3.8% | %
Marketing Rate | 2% | %
Financing Rate | 8.5% | %
Loan to Cost | 75% | %
Construction Duration | 24 | months
Bridge Loan Duration | 9 | months
PROJECT TOTALS
Total Hard Costs |  |  | From Hard Costs sheet
Total Soft Costs |  |  | From Soft Costs sheet
SC Cash Payments |  |  | Cash paid to land partner
TOTAL PROJECT COST |  | 100.0% | From Summary sheet
Total Revenue |  |  | From Revenue sheet
Gross Profit |  |  | From Summary sheet
ROI (Return on Cost) |  |  | Profit / Total Cost
SYNAGOGUE/MIKVAH (Unit #51)
Synagogue Revenue (at cost) |  |  | 10,500 NSF @ $400/SF
Allocated Cost (part of Hard+Soft) |  |  | Paid by SC from windfall
Net Impact on Profit | 0 | 0.0% | Revenue = Cost (break-even)
Revenue-Generating Units | 50 |  | Excludes Synagogue/Mikvah
Cost per Revenue Unit |  |  | From Summary sheet
NAMED RANGES - How Formulas Connect Sheets
Range Name | Location | Value | Description
LandPartner_Land | B11 |  | 80% - SC land in-kind ($8M)
LandPartner_Cash1 | B12 |  | 62.5% - SC cash Month 0 ($1.25M)
LandPartner_Cash2 | B13 |  | 37.5% - SC cash Month 6 ($750K)
TotalHardCosts | 'Hard Costs'!E[row] |  | ~85% - All construction costs
TotalSoftCosts | 'Soft Costs'!B[row] |  | ~12% - Design, permits, financing
TotalRevenue | 'Revenue'!F[row] |  | 100% - Total project revenue
GC_OHP | B18 |  | 10% - GC overhead & profit rate
AE_Rate | B23 |  | 3.8% - Architecture & engineering fee
Marketing_Rate | B24 |  | 2.0% - Marketing & sales rate
LTC | B26 |  | 75% - Loan-to-cost ratio
HOW TO USE NAMED RANGES: |  |  | Type = then the range name in any formula
Example:

## Hard Costs - Simplified
HARD COSTS - SIMPLIFIED (7 MAJOR CATEGORIES)
Consolidated from 23 CSI divisions for clarity
Category | Description | Rate ($/GSF) | GSF | Total Cost
1 | SITE & FOUNDATION | 18.89 | 108675
Site work, demolition, earthwork, utilities connections (CSI 01, 02, 31)
2 | STRUCTURE | 46.92 | 108675
Concrete structure, structural steel, framing (CSI 03, 05)
3 | BUILDING ENVELOPE | 46.31 | 108675
Masonry, waterproofing, roofing, windows, doors (CSI 04, 07, 08)
4 | INTERIOR FINISHES | 48.56 | 108675
Drywall, flooring, paint, millwork, cabinets, specialties (CSI 06, 09, 10, 11, 12, 13)
5 | MECHANICAL, PLUMBING & FIRE PROTECTION | 28.5 | 108675
HVAC, plumbing, fire sprinklers (CSI 21, 22, 23)
6 | ELECTRICAL & LOW VOLTAGE | 16.65 | 108675
Power, lighting, data, phone, security, fire alarm (CSI 26, 27, 28)
7 | ELEVATORS & SITE IMPROVEMENTS | 9.13 | 108675
Elevators, landscaping, paving, site utilities (CSI 14, 32, 33)
SUBTOTAL - Direct Construction Costs
GENERAL CONDITIONS (9%)
Site office, supervision, permits, safety
OVERHEAD & PROFIT (10%)
GC's business costs, insurance, profit margin
SUBTOTAL before Contingencies
DESIGN CONTINGENCY (8%)
Buffer for design changes during construction
CONSTRUCTION CONTINGENCY (5%)
Unexpected field conditions (rock, utilities, etc.)
OWNER CONTINGENCY (3%)
Owner's reserve for changes/upgrades
TOTAL HARD COSTS
Cost per GSF
Detailed CSI Budget (23 divisions)
Simplified Budget (7 categories)
Difference

## Hard Costs
HARD COSTS - CSI MASTERFORMAT DIVISIONS
CSI | Description | Rate ($/GSF) | GSF | Total Cost
01 | General Requirements | 10.53
02 | Existing Conditions & Site Work | 4.56
03 | Concrete - Pour-in-Place PT | 39.47
04 | Masonry | 2.46
05 | Metals | 7.45
06 | Wood & Plastics | 2.81
07 | Thermal & Moisture Protection | 19.3
08 | Openings (Doors, Windows, HVHZ) | 24.55
09 | Finishes | 36.83
10 | Specialties | 3.95
11 | Equipment | 3.33
12 | Furnishings | 1.05
13 | Special Construction | 1.58
14 | Conveying Equipment | 2.72
21 | Fire Suppression | 6.58
22 | Plumbing | 8.77
23 | HVAC | 13.15
26 | Electrical | 13.15
27 | Communications | 1.75
28 | Electronic Safety & Security | 1.75
31 | Earthwork | 3.68
32 | Exterior Improvements | 3.51
33 | Utilities | 2.81
SUBTOTAL - Construction
General Conditions
Overhead & Profit
Subtotal before Contingency
Design Contingency
Construction Contingency
Owner Contingency
TOTAL HARD COSTS
Cost per GSF

## Soft Costs
SOFT COSTS - PAYMENT TIMING
CASH: Months 1-12 ¦ IN-KIND: Months 7-24 ¦ Financing: Dynamic
Category | Amount | Payment Timing | Basis
IN-KIND SOFT COSTS (Months 7-24)
Architecture & Engineering |  | IN-KIND (Mo 7-24) | 3.35% of hard costs
Marketing & Sales |  | IN-KIND (Mo 7-24) | 2.09% of hard costs
Legal & Accounting |  | IN-KIND (Mo 7-24) | 0.83% of hard costs
Developer Fee |  | IN-KIND (Mo 7-24) | 1.26% of hard costs
SUBTOTAL IN-KIND |  |  | 18 months (Mo 7-24)
CASH SOFT COSTS (Months 1-12)
Building Permit |  | CASH (Mo 1-12) | 1.26% of hard costs
Impact Fees |  | CASH (Mo 1-12) | 0.83% of hard costs
Plan Review |  | CASH (Mo 1-12) | 0.41% of hard costs
Insurance |  | CASH (Mo 1-12) | 0.67% of hard costs
Testing & Inspections |  | CASH (Mo 1-12) | 0.24% of hard costs
Utilities & Misc |  | CASH (Mo 1-12) | 0.16% of hard costs
SUBTOTAL CASH |  |  | 12 months (Mo 1-12)
FINANCING COSTS (Dynamic)
Bridge Loan Interest |  | Variable (9%/yr) | Calculated in Cash Flow sheet
SUBTOTAL SOFT COSTS (Before Financing)
TOTAL SOFT COSTS (With Financing)
% of Hard Costs |  |  | Target: 12.0%
Cost per GSF

## Revenue
REVENUE ANALYSIS
Floor | Unit Type | Units | NSF | $/SF | Total Revenue
4-5 | Hospitality 2BR/1.5BA | 32 | 25200 | 1200
6 | Hospitality 2BR/1.5BA | 10 | 8680 | 1200
7 | Condos 3BR/2BA | 8 | 8680 | 1200
1 | Chabad/Mikvah (at cost) | 1 | 10500 | 400
TOTAL REVENUE

## Project Deal Structure
NEVO TOWER - PROJECT DEAL STRUCTURE
Complete Partnership Structure, Financing, and Payout Waterfall
THE PARTIES
Simcha Connection (SC) | Land Owner - 1580 79th St, North Bay Village |  | $10M land value
Developer Partner | Development partner sought by SC |  | Cash + expertise
Partnership is 50/50 profit split AFTER obligations
SC CONTRIBUTIONS & PAYMENTS
Item | Amount | Timing | Type | Interest?
Land (In-Kind) | $8,000,000 | Upfront | Equity contribution | NO
Cash to SC from Dev | $1,250,000 | Month 0 (key money) | Cash OUT to SC | N/A
Cash to SC from Dev | $750,000 | Month 6 | Cash OUT to SC | N/A
Land Payment AT EXIT | $8,000,000 | After all vendors paid | From windfall | NO!
FINANCING STRUCTURE
Source | Amount | Duration | Purpose | Cost
Developer Cash OUT to SC | $2,000,000 | Upfront | SC receives cash payments | $0
Bridge Loan | ~$6,600,000 | 9 months | Construction subtotal only | ~$420K
Pre-Sales Deposits | ~$14,700,000 | Months 1-24 | Remaining construction | $0
Vendor Terms | Variable | Ongoing | GC/OH&P/Contingencies | $0
In-Kind Suppliers | Variable | Ongoing | Materials at cost | $0
KEY POINT: | Pre-sales from Month 10+ cover ALL remaining construction costs
PAYMENT WATERFALL (AT PROJECT EXIT)
Priority | Payee | Amount | Description
0 | Total Revenue | $55,272,000 | Gross sales revenue from 50 units
1 | Bridge Loan Payoff | ~$420,000 | Principal + interest (if balance remains)
2 | Vendors/Contractors | ~$32,609,001 | All construction costs paid
3 | Soft Costs | ~$4,600,000 | A&E, marketing, permits, etc.
4 | SC Land Payment | $8,000,000 | NO INTEREST! Paid from windfall
5 | Remaining Windfall | ~$9,643,000 | Available for profit split
6 | SC Share (50%) | ~$4,821,500 | 50% of windfall after all obligations
7 | Developer Share (50%) | ~$4,821,500 | 50% of windfall after all obligations
DEVELOPER ECONOMICS
Cash OUT (Investment to SC) | $2,000,000 |  | Paid to SC upfront
Cash IN (Return) | ~$4,821,500 |  | 50% of windfall
Net Profit | ~$2,821,500 |  | $4.82M - $2M investment
ROI | 141% |  | $2.82M profit / $2M investment
KEY DEAL BENEFITS
✓ NO INTEREST on $8M SC land payment | Massive savings vs traditional land purchase
✓ Bridge loan only 9 months | Pre-sales cover construction from Month 10+
✓ Vendor payment terms | GC/OH&P/contingencies funded by terms, not loan
✓ In-kind supplier opportunities | Reduce cash needed with material contributions
✓ 141% ROI on $2M investment | Developer gets $4.82M from $2M investment
✓ Pre-sales de-risk project | Units sold before completion = guaranteed revenue

## 24-Month Cash Flow
NEVO TOWER - 24-MONTH CASH FLOW WITH PRE-SALES
CASH (Mo 1-12) ¦ IN-KIND (Mo 7-24) ¦ Financing calculated dynamically
Month | Activity | Hard Cost | CASH Soft | IN-KIND Soft | SC Cash | Units Sold | Pre-Sales $ | Usable (90%) | Cash IN | Net Flow | Cumulative | Bridge Bal | Interest | Final Cum
1 | Foundation |  |  | 0 |  | 1
2 | Foundation |  |  | 0 | 0 | 2
3 | Site Work |  |  | 0 | 0 | 2
4 | Site Work |  |  | 0 | 0 | 3
5 | Superstructure |  |  | 0 | 0 | 3
6 | Superstructure |  |  | 0 |  | 3
7 | Superstructure |  |  |  | 0 | 4
8 | Superstructure |  |  |  | 0 | 4
9 | Envelope |  |  |  | 0 | 4
10 | Envelope |  |  |  | 0 | 4
11 | MEP Rough-In |  |  |  | 0 | 3
12 | MEP Rough-In |  |  |  | 0 | 3
13 | MEP Install |  | 0 |  | 0 | 2
14 | MEP Install |  | 0 |  | 0 | 2
15 | Interior Framing |  | 0 |  | 0 | 2
16 | Interior Framing |  | 0 |  | 0 | 2
17 | Finishes |  | 0 |  | 0 | 1
18 | Finishes |  | 0 |  | 0 | 1
19 | Fixtures |  | 0 |  | 0 | 1
20 | Fixtures |  | 0 |  | 0 | 1
21 | Closeout |  | 0 |  | 0 | 1
22 | Punch List |  | 0 |  | 0 | 1
23 | Final Inspection |  | 0 |  | 0 | 0
24 | CO & Turnover |  | 0 |  | 0 | 0
TOTALS:
MAX BRIDGE LOAN NEEDED:
TOTAL FINANCING COSTS (9% Interest):
TIE-OUT: FINAL CUMULATIVE = GROSS PROFIT | Final Cumulative (Month 24) = |  | Gross Profit (Summary) = |  | Difference =

## GC RFQ Summary
GENERAL CONTRACTOR - REQUEST FOR QUOTE SUMMARY
NEVO Tower - 1580 79th St Causeway, North Bay Village, FL
Total Project: 108,675 GSF ¦ 7 Stories + Rooftop ¦ 50 Residential Units
CSI DIVISION BREAKDOWN - MATERIALS, LABOR & WORKFORCE
CSI | Description | Total Cost | Materials % | Labor % | Man-Hours | Worker Type | Crew Size
01 | General Requirements |  | 40% | 60% | 15257 | Project Management/Supervisors | 5-8
02 | Site Work & Demolition |  | 30% | 70% | 7708 | Laborers/Equipment Operators | 6-10
03 | Concrete - PT Structure |  | 45% | 55% | 52426 | Concrete Workers/Ironworkers | 15-25
04 | Masonry |  | 50% | 50% | 2970 | Masons/Laborers | 4-6
05 | Metals & Structural Steel |  | 65% | 35% | 6297 | Ironworkers/Welders | 6-10
06 | Wood & Plastics |  | 55% | 45% | 3053 | Carpenters | 4-6
07 | Waterproofing & Roofing |  | 40% | 60% | 27965 | Roofers/Waterproofing Specialists | 6-10
08 | Doors, Windows & HVHZ Glazing |  | 70% | 30% | 17786 | Glaziers/Installation Specialists | 8-12
09 | Interior Finishes |  | 45% | 55% | 48919 | Carpenters/Painters/Drywall | 20-30
10 | Specialties |  | 75% | 25% | 2384 | Specialty Installers | 2-4
11 | Equipment |  | 80% | 20% | 1608 | Equipment Installers | 2-4
12 | Furnishings |  | 85% | 15% | 380 | Installers | 2-3
13 | Special Construction |  | 60% | 40% | 1526 | Specialty Contractors | 3-5
14 | Elevators |  | 75% | 25% | 1871 | Elevator Mechanics/Technicians | 4-6
21 | Fire Suppression |  | 50% | 50% | 7945 | Pipefitters/Sprinkler Fitters | 4-6
22 | Plumbing |  | 45% | 55% | 11648 | Plumbers/Pipefitters | 6-10
23 | HVAC |  | 50% | 50% | 15878 | HVAC Technicians/Sheet Metal | 8-12
26 | Electrical |  | 40% | 60% | 19054 | Electricians/Low Voltage Tech | 10-15
27 | Communications & Data |  | 60% | 40% | 1690 | Low Voltage Technicians | 3-5
28 | Security & Fire Alarm |  | 65% | 35% | 1479 | Security/Fire Alarm Techs | 3-4
31 | Earthwork |  | 25% | 75% | 6665 | Equipment Operators/Laborers | 6-8
32 | Exterior Improvements |  | 50% | 50% | 4238 | Landscapers/Pavers/Masons | 6-10
33 | Utilities |  | 55% | 45% | 3053 | Utility Workers/Excavators | 4-6
SUBTOTAL - Direct Costs
| General Conditions (9%) |  |  |  | 13090 | Project Manager/Super/Admin
Overhead & Profit (10%)
Contingencies (16%)
TOTAL HARD COSTS
WORKFORCE SUMMARY
Category | Worker Types | Est. Man-Hours | Avg Rate/Hr | Total Labor Cost | Peak Workers | Duration
Skilled Trades | Concrete, Ironworkers, Electricians, Plumbers, HVAC | 130900 | 55 |  |  | 18-24 months
Semi-Skilled | Carpenters, Masons, Painters, Drywall | 65450 | 40 |  |  | 12-20 months
Laborers | General Labor, Site Work, Material Handling | 39270 | 30 |  |  | 1-24 months
Specialists | Glaziers, Waterproofing, Elevator Techs | 20944 | 60 |  |  | 8-18 months
Management/Super | PM, Superintendent, Foremen, Admin | 5236 | 75 |  |  | 1-24 months
TOTAL WORKFORCE

## Sync Instructions
HOW TO KEEP THIS WORKBOOK IN SYNC
YELLOW CELLS = EDITABLE | You can change these values
When you edit a yellow cell: | All formulas update automatically
Named Ranges: | Connect sheets together
Example: | TotalHardCosts pulls from Hard Costs sheet
To regenerate this file: | Run scripts/make_interactive_workbook_v3.py
ALL 11 CORRECTIONS APPLIED:
1. Summary - % in column C | ✓
2. Assumptions - % in columns C & D | ✓
3. Soft costs = 12% of project cost | ✓
4. All formulas use named ranges | ✓
5. Cash flow with formulas & 50 units | ✓
6. SC Cash OUT label corrected | ✓
7. Auto-fit columns | ✓
8. SF with commas throughout | ✓
9. Soft costs categorized IN-KIND/CASH | ✓
10. Project deal sheet corrected | ✓
11. All sheets formatted properly | ✓

## Measurements 50
Floor # | Saleable | Height | Width | Length | Floor Plate GSF | %GSF | Floor Plate NSF | %NSF | Unit Size NSF | Units per Floor | USE | Units by Use | GSF by Use | Cost by SF | Unit Cost | Total Floor Cost | Soft Cost | Sell by SF | Unit Sale | Total Floor Sale | Gross Profit | GP % | address
1 | Saleable @Cost | 12 | 75 | 175 | [5 empty] | 1 | Chabad House - Mikvah |  |  | 300.0585 |  |  |  | 400 |  |  |  |  | 1580 79st. causeway, North Bay Village, FL 33141
2 | Non-Saleable | 9 | 90 | 175 | [5 empty] | 51 | Parking - EV Stations / ADA |  |  | 300.06
3 | Non-Saleable | 9 | 90 | 175 | [5 empty] | 51 | Parking - EV Stations / ADA |  |  | 300.06
4 | Saleable | 10 | 90 | 175 | [5 empty] | 16 | Residential Hospitality 2 bed-1.5 bath |  |  | 300.06 |  |  |  | 1200
5 | Saleable | 10 | 90 | 175 | [5 empty] | 16 | Residential Hospitality 2 bed-1.5 bath |  |  | 300.06 |  |  |  | 1200
6 | Saleable | 10 | 70 | 155 | [5 empty] | 10 | Residential Hospitality 2 bed-1.5 bath |  |  | 300.06 |  |  |  | 1200
7 | Saleable | 10 | 70 | 155 | [5 empty] | 8 | Residential Condos 3 bed / 2 bath |  |  | 300.06 |  |  |  | 1200
roof top | Non-Saleable | 5 | 70 | 155 | [5 empty] | 1 | Pool - Gym |  |  | 300.06
Total