## Summary
NEVO TOWER - EXECUTIVE SUMMARY
Generated: 2025-11-06 03:56
TOTAL DEVELOPMENT COST
SC Cash Payment (Project Cost)
Hard Costs
Soft Costs
TOTAL PROJECT COST | 100.0%
REVENUE
Total Revenue
PROFITABILITY
Gross Profit
Profit Margin
Return on Cost (ROI)
Cost per Unit (50 Condos) |  | Excluding synagogue cost
Cost per NSF
Revenue per NSF

## Assumptions
NEVO TOWER - PROJECT ASSUMPTIONS
PROJECT INFORMATION
Total GSF | 108675 | 100%
Total NSF | 86940
Residential Units | 50 | 100%
LAND PARTNER STRUCTURE
Land Partner - Land (In-Kind) | 8000000 |  | Land value $10M total - $2M paid cash
SC Key Money (Month 0) | 1250000 |  | Developer pays SC to enter deal
SC Payment (Month 6) | 750000 |  | Additional payment to SC
Land Partner - Deferred Payment | 0 | 0% | $8M paid at exit (NOT a cost)
COST ASSUMPTIONS
GC Overhead & Profit | 10% | %
General Conditions | 9% | %
Design Contingency | 8% | %
Construction Contingency | 5% | %
Owner Contingency | 3% | %
A&E Fee Rate | 3.8% | %
Marketing Rate | 2% | %
Financing Rate | 8.5% | %
Loan to Cost | 75% | %
Construction Duration | 24 | months
Bridge Loan Duration | 9 | months
PROJECT TOTALS
Total Hard Costs |  |  | From Hard Costs sheet
Total Soft Costs |  |  | From Soft Costs sheet
SC Cash Payments |  |  | Cash paid to land partner
TOTAL PROJECT COST |  | 100.0% | From Summary sheet
Total Revenue |  |  | From Revenue sheet
Gross Profit |  |  | From Summary sheet
ROI (Return on Cost) |  |  | Profit / Total Cost
SYNAGOGUE/MIKVAH (Unit #51)
Synagogue Revenue (at cost) |  |  | 10,500 NSF @ $400/SF
Allocated Cost (part of Hard+Soft) |  |  | Paid by SC from windfall
Net Impact on Profit | 0 | 0.0% | Revenue = Cost (break-even)
Revenue-Generating Units | 50 |  | Excludes Synagogue/Mikvah
Cost per Revenue Unit |  |  | From Summary sheet
NAMED RANGES - How Formulas Connect Sheets
Range Name | Location | Value | Description
LandPartner_Land | B11 |  | 80% - SC land in-kind ($8M)
LandPartner_Cash1 | B12 |  | 62.5% - SC cash Month 0 ($1.25M)
LandPartner_Cash2 | B13 |  | 37.5% - SC cash Month 6 ($750K)
TotalHardCosts | 'Hard Costs'!E[row] |  | ~85% - All construction costs
TotalSoftCosts | 'Soft Costs'!B[row] |  | ~12% - Design, permits, financing
TotalRevenue | 'Revenue'!F[row] |  | 100% - Total project revenue
GC_OHP | B18 |  | 10% - GC overhead & profit rate
AE_Rate | B23 |  | 3.8% - Architecture & engineering fee
Marketing_Rate | B24 |  | 2.0% - Marketing & sales rate
LTC | B26 |  | 75% - Loan-to-cost ratio
HOW TO USE NAMED RANGES: |  |  | Type = then the range name in any formula
Example:

## Hard Costs - APC Filigree
HARD COSTS - APC FILIGREE PRECAST SYSTEM
Aerial Precast Concrete Composite Deck System - Reduced Labor & Time
CSI | Description | Rate ($/GSF) | GSF | Total Cost | vs Traditional
01 | General Requirements | 10.53 | 108675 |  | Same
02 | Existing Conditions & Site Work | 4.56 | 108675 |  | Same
03 | APC Filigree Precast System | 31.58 | 108675 |  | 20% savings
04 | Masonry | 2.46 | 108675 |  | Same
05 | Structural Steel (integrated) | 5.96 | 108675 |  | 20% savings
06 | Wood & Plastics | 2.81 | 108675 |  | Same
07 | Thermal & Moisture Protection | 19.3 | 108675 |  | Same
08 | Openings (Doors, Windows, HVHZ) | 24.55 | 108675 |  | Same
09 | Finishes | 36.83 | 108675 |  | Same
10 | Specialties | 3.95 | 108675 |  | Same
11 | Equipment | 3.33 | 108675 |  | Same
12 | Furnishings | 1.05 | 108675 |  | Same
13 | Special Construction | 1.58 | 108675 |  | Same
14 | Conveying Equipment | 2.72 | 108675 |  | Same
21 | Fire Suppression | 6.58 | 108675 |  | Same
22 | Plumbing | 7.89 | 108675 |  | 10% savings - embedded in slab
23 | HVAC | 13.15 | 108675 |  | Same
26 | Electrical | 11.84 | 108675 |  | 10% savings - conduits in slab
27 | Communications | 1.75 | 108675 |  | Same
28 | Electronic Safety & Security | 1.75 | 108675 |  | Same
31 | Earthwork | 3.68 | 108675 |  | Same
32 | Exterior Improvements | 3.51 | 108675 |  | Same
33 | Utilities | 2.81 | 108675 |  | Same
SUBTOTAL - Construction
| Traditional PT System Cost |  |  | 23445544.5 | For reference
APC Filigree System Cost
| SAVINGS |  |  |  | 5.4% reduction
General Conditions
Overhead & Profit
Subtotal before Contingency
Design Contingency
Construction Contingency
Owner Contingency
TOTAL HARD COSTS (APC Filigree)
Cost per GSF
Traditional System Total
APC Filigree Total
TOTAL PROJECT SAVINGS

## Hard Costs
HARD COSTS - CSI MASTERFORMAT DIVISIONS
CSI | Description | Rate ($/GSF) | GSF | Total Cost
01 | General Requirements | 10.53
02 | Existing Conditions & Site Work | 4.56
03 | Concrete - Pour-in-Place PT | 39.47
04 | Masonry | 2.46
05 | Metals | 7.45
06 | Wood & Plastics | 2.81
07 | Thermal & Moisture Protection | 19.3
08 | Openings (Doors, Windows, HVHZ) | 24.55
09 | Finishes | 36.83
10 | Specialties | 3.95
11 | Equipment | 3.33
12 | Furnishings | 1.05
13 | Special Construction | 1.58
14 | Conveying Equipment | 2.72
21 | Fire Suppression | 6.58
22 | Plumbing | 8.77
23 | HVAC | 13.15
26 | Electrical | 13.15
27 | Communications | 1.75
28 | Electronic Safety & Security | 1.75
31 | Earthwork | 3.68
32 | Exterior Improvements | 3.51
33 | Utilities | 2.81
SUBTOTAL - Construction
General Conditions
Overhead & Profit
Subtotal before Contingency
Design Contingency
Construction Contingency
Owner Contingency
TOTAL HARD COSTS
Cost per GSF

## Soft Costs
SOFT COSTS - PAYMENT TIMING
CASH: Months 1-12 ¦ IN-KIND: Months 7-24 ¦ Financing: Dynamic
Category | Amount | Payment Timing | Basis
IN-KIND SOFT COSTS (Months 7-24)
Architecture & Engineering |  | IN-KIND (Mo 7-24) | 3.35% of hard costs
Marketing & Sales |  | IN-KIND (Mo 7-24) | 2.09% of hard costs
Legal & Accounting |  | IN-KIND (Mo 7-24) | 0.83% of hard costs
Developer Fee |  | IN-KIND (Mo 7-24) | 1.26% of hard costs
SUBTOTAL IN-KIND |  |  | 18 months (Mo 7-24)
CASH SOFT COSTS (Months 1-12)
Building Permit |  | CASH (Mo 1-12) | 1.26% of hard costs
Impact Fees |  | CASH (Mo 1-12) | 0.83% of hard costs
Plan Review |  | CASH (Mo 1-12) | 0.41% of hard costs
Insurance |  | CASH (Mo 1-12) | 0.67% of hard costs
Testing & Inspections |  | CASH (Mo 1-12) | 0.24% of hard costs
Utilities & Misc |  | CASH (Mo 1-12) | 0.16% of hard costs
SUBTOTAL CASH |  |  | 12 months (Mo 1-12)
FINANCING COSTS (Dynamic)
Bridge Loan Interest |  | Variable (9%/yr) | Calculated in Cash Flow sheet
SUBTOTAL SOFT COSTS (Before Financing)
TOTAL SOFT COSTS (With Financing)
% of Hard Costs |  |  | Target: 12.0%
Cost per GSF

## Revenue
REVENUE ANALYSIS
Floor | Unit Type | Units | NSF | $/SF | Total Revenue
4-5 | Hospitality 2BR/1.5BA | 32 | 25200 | 1200
6 | Hospitality 2BR/1.5BA | 10 | 8680 | 1200
7 | Condos 3BR/2BA | 8 | 8680 | 1200
1 | Chabad/Mikvah (at cost) | 1 | 10500 | 400
TOTAL REVENUE

## Project Deal Structure
NEVO TOWER - PROJECT DEAL STRUCTURE
Complete Partnership Structure, Financing, and Payout Waterfall
THE PARTIES
Simcha Connection (SC) | Land Owner - 1580 79th St, North Bay Village |  | $10M land value
Developer Partner | Development partner sought by SC |  | Cash + expertise
Partnership is 50/50 profit split AFTER obligations
SC CONTRIBUTIONS & PAYMENTS
Item | Amount | Timing | Type | Interest?
Land (In-Kind) | $8,000,000 | Upfront | Equity contribution | NO
Cash to SC from Dev | $1,250,000 | Month 0 (key money) | Cash OUT to SC | N/A
Cash to SC from Dev | $750,000 | Month 6 | Cash OUT to SC | N/A
Land Payment AT EXIT | $8,000,000 | After all vendors paid | From windfall | NO!
FINANCING STRUCTURE
Source | Amount | Duration | Purpose | Cost
Developer Cash OUT to SC | $2,000,000 | Upfront | SC receives cash payments | $0
Bridge Loan | ~$6,600,000 | 9 months | Construction subtotal only | ~$420K
Pre-Sales Deposits | ~$14,700,000 | Months 1-24 | Remaining construction | $0
Vendor Terms | Variable | Ongoing | GC/OH&P/Contingencies | $0
In-Kind Suppliers | Variable | Ongoing | Materials at cost | $0
KEY POINT: | Pre-sales from Month 10+ cover ALL remaining construction costs
PAYMENT WATERFALL (AT PROJECT EXIT)
Priority | Payee | Amount | Description
0 | Total Revenue | $55,272,000 | Gross sales revenue from 50 units
1 | Bridge Loan Payoff | ~$420,000 | Principal + interest (if balance remains)
2 | Vendors/Contractors | ~$32,609,001 | All construction costs paid
3 | Soft Costs | ~$4,600,000 | A&E, marketing, permits, etc.
4 | SC Land Payment | $8,000,000 | NO INTEREST! Paid from windfall
5 | Remaining Windfall | ~$9,643,000 | Available for profit split
6 | SC Share (50%) | ~$4,821,500 | 50% of windfall after all obligations
7 | Developer Share (50%) | ~$4,821,500 | 50% of windfall after all obligations
DEVELOPER ECONOMICS
Cash OUT (Investment to SC) | $2,000,000 |  | Paid to SC upfront
Cash IN (Return) | ~$4,821,500 |  | 50% of windfall
Net Profit | ~$2,821,500 |  | $4.82M - $2M investment
ROI | 141% |  | $2.82M profit / $2M investment
KEY DEAL BENEFITS
✓ NO INTEREST on $8M SC land payment | Massive savings vs traditional land purchase
✓ Bridge loan only 9 months | Pre-sales cover construction from Month 10+
✓ Vendor payment terms | GC/OH&P/contingencies funded by terms, not loan
✓ In-kind supplier opportunities | Reduce cash needed with material contributions
✓ 141% ROI on $2M investment | Developer gets $4.82M from $2M investment
✓ Pre-sales de-risk project | Units sold before completion = guaranteed revenue

## 24-Month Cash Flow
NEVO TOWER - 24-MONTH CASH FLOW WITH PRE-SALES
CASH (Mo 1-12) ¦ IN-KIND (Mo 7-24) ¦ Financing calculated dynamically
Month | Activity | Hard Cost | CASH Soft | IN-KIND Soft | SC Cash | Units Sold | Pre-Sales $ | Usable (90%) | Cash IN | Net Flow | Cumulative | Bridge Bal | Interest | Final Cum
1 | Foundation |  |  | 0 |  | 1
2 | Foundation |  |  | 0 | 0 | 2
3 | Site Work |  |  | 0 | 0 | 2
4 | Site Work |  |  | 0 | 0 | 3
5 | Superstructure |  |  | 0 | 0 | 3
6 | Superstructure |  |  | 0 |  | 3
7 | Superstructure |  |  |  | 0 | 4
8 | Superstructure |  |  |  | 0 | 4
9 | Envelope |  |  |  | 0 | 4
10 | Envelope |  |  |  | 0 | 4
11 | MEP Rough-In |  |  |  | 0 | 3
12 | MEP Rough-In |  |  |  | 0 | 3
13 | MEP Install |  | 0 |  | 0 | 2
14 | MEP Install |  | 0 |  | 0 | 2
15 | Interior Framing |  | 0 |  | 0 | 2
16 | Interior Framing |  | 0 |  | 0 | 2
17 | Finishes |  | 0 |  | 0 | 1
18 | Finishes |  | 0 |  | 0 | 1
19 | Fixtures |  | 0 |  | 0 | 1
20 | Fixtures |  | 0 |  | 0 | 1
21 | Closeout |  | 0 |  | 0 | 1
22 | Punch List |  | 0 |  | 0 | 1
23 | Final Inspection |  | 0 |  | 0 | 0
24 | CO & Turnover |  | 0 |  | 0 | 0
TOTALS:
MAX BRIDGE LOAN NEEDED:
TOTAL FINANCING COSTS (9% Interest):
TIE-OUT: FINAL CUMULATIVE = GROSS PROFIT | Final Cumulative (Month 24) = |  | Gross Profit (Summary) = |  | Difference =

## GC RFQ Summary
GENERAL CONTRACTOR - REQUEST FOR QUOTE SUMMARY
NEVO Tower - 1580 79th St Causeway, North Bay Village, FL
Total Project: 108,675 GSF ¦ 7 Stories + Rooftop ¦ 50 Residential Units
CSI DIVISION BREAKDOWN - MATERIALS, LABOR & WORKFORCE
CSI | Description | Total Cost | Materials % | Labor % | Man-Hours | Worker Type | Crew Size
01 | General Requirements |  | 40% | 60% | 15257 | Project Management/Supervisors | 5-8
02 | Site Work & Demolition |  | 30% | 70% | 7708 | Laborers/Equipment Operators | 6-10
03 | Concrete - PT Structure |  | 45% | 55% | 52426 | Concrete Workers/Ironworkers | 15-25
04 | Masonry |  | 50% | 50% | 2970 | Masons/Laborers | 4-6
05 | Metals & Structural Steel |  | 65% | 35% | 6297 | Ironworkers/Welders | 6-10
06 | Wood & Plastics |  | 55% | 45% | 3053 | Carpenters | 4-6
07 | Waterproofing & Roofing |  | 40% | 60% | 27965 | Roofers/Waterproofing Specialists | 6-10
08 | Doors, Windows & HVHZ Glazing |  | 70% | 30% | 17786 | Glaziers/Installation Specialists | 8-12
09 | Interior Finishes |  | 45% | 55% | 48919 | Carpenters/Painters/Drywall | 20-30
10 | Specialties |  | 75% | 25% | 2384 | Specialty Installers | 2-4
11 | Equipment |  | 80% | 20% | 1608 | Equipment Installers | 2-4
12 | Furnishings |  | 85% | 15% | 380 | Installers | 2-3
13 | Special Construction |  | 60% | 40% | 1526 | Specialty Contractors | 3-5
14 | Elevators |  | 75% | 25% | 1871 | Elevator Mechanics/Technicians | 4-6
21 | Fire Suppression |  | 50% | 50% | 7945 | Pipefitters/Sprinkler Fitters | 4-6
22 | Plumbing |  | 45% | 55% | 11648 | Plumbers/Pipefitters | 6-10
23 | HVAC |  | 50% | 50% | 15878 | HVAC Technicians/Sheet Metal | 8-12
26 | Electrical |  | 40% | 60% | 19054 | Electricians/Low Voltage Tech | 10-15
27 | Communications & Data |  | 60% | 40% | 1690 | Low Voltage Technicians | 3-5
28 | Security & Fire Alarm |  | 65% | 35% | 1479 | Security/Fire Alarm Techs | 3-4
31 | Earthwork |  | 25% | 75% | 6665 | Equipment Operators/Laborers | 6-8
32 | Exterior Improvements |  | 50% | 50% | 4238 | Landscapers/Pavers/Masons | 6-10
33 | Utilities |  | 55% | 45% | 3053 | Utility Workers/Excavators | 4-6
SUBTOTAL - Direct Costs
| General Conditions (9%) |  |  |  | 13090 | Project Manager/Super/Admin
Overhead & Profit (10%)
Contingencies (16%)
TOTAL HARD COSTS
WORKFORCE SUMMARY
Category | Worker Types | Est. Man-Hours | Avg Rate/Hr | Total Labor Cost | Peak Workers | Duration
Skilled Trades | Concrete, Ironworkers, Electricians, Plumbers, HVAC | 130900 | 55 |  |  | 18-24 months
Semi-Skilled | Carpenters, Masons, Painters, Drywall | 65450 | 40 |  |  | 12-20 months
Laborers | General Labor, Site Work, Material Handling | 39270 | 30 |  |  | 1-24 months
Specialists | Glaziers, Waterproofing, Elevator Techs | 20944 | 60 |  |  | 8-18 months
Management/Super | PM, Superintendent, Foremen, Admin | 5236 | 75 |  |  | 1-24 months
TOTAL WORKFORCE

## Sync Instructions
HOW TO KEEP THIS WORKBOOK IN SYNC
YELLOW CELLS = EDITABLE | You can change these values
When you edit a yellow cell: | All formulas update automatically
Named Ranges: | Connect sheets together
Example: | TotalHardCosts pulls from Hard Costs sheet
To regenerate this file: | Run scripts/make_interactive_workbook_v3.py
ALL 11 CORRECTIONS APPLIED:
1. Summary - % in column C | ✓
2. Assumptions - % in columns C & D | ✓
3. Soft costs = 12% of project cost | ✓
4. All formulas use named ranges | ✓
5. Cash flow with formulas & 50 units | ✓
6. SC Cash OUT label corrected | ✓
7. Auto-fit columns | ✓
8. SF with commas throughout | ✓
9. Soft costs categorized IN-KIND/CASH | ✓
10. Project deal sheet corrected | ✓
11. All sheets formatted properly | ✓

## Measurements 50
Floor # | Saleable | Height | Width | Length | Floor Plate GSF | %GSF | Floor Plate NSF | %NSF | Unit Size NSF | Units per Floor | USE | Units by Use | GSF by Use | Cost by SF | Unit Cost | Total Floor Cost | Soft Cost | Sell by SF | Unit Sale | Total Floor Sale | Gross Profit | GP % | address
1 | Saleable @Cost | 12 | 75 | 175 | [5 empty] | 1 | Chabad House - Mikvah |  |  | 300.0585 |  |  |  | 400 |  |  |  |  | 1580 79st. causeway, North Bay Village, FL 33141
2 | Non-Saleable | 9 | 90 | 175 | [5 empty] | 51 | Parking - EV Stations / ADA |  |  | 300.06
3 | Non-Saleable | 9 | 90 | 175 | [5 empty] | 51 | Parking - EV Stations / ADA |  |  | 300.06
4 | Saleable | 10 | 90 | 175 | [5 empty] | 16 | Residential Hospitality 2 bed-1.5 bath |  |  | 300.06 |  |  |  | 1200
5 | Saleable | 10 | 90 | 175 | [5 empty] | 16 | Residential Hospitality 2 bed-1.5 bath |  |  | 300.06 |  |  |  | 1200
6 | Saleable | 10 | 70 | 155 | [5 empty] | 10 | Residential Hospitality 2 bed-1.5 bath |  |  | 300.06 |  |  |  | 1200
7 | Saleable | 10 | 70 | 155 | [5 empty] | 8 | Residential Condos 3 bed / 2 bath |  |  | 300.06 |  |  |  | 1200
roof top | Non-Saleable | 5 | 70 | 155 | [5 empty] | 1 | Pool - Gym |  |  | 300.06
Total

## RFQ - APC Filigree Detail
REQUEST FOR QUOTE - APC FILIGREE PRECAST SYSTEM
NEVO Tower - 1580 79th St Causeway, North Bay Village, FL
Total Project: 108,675 GSF ¦ 7 Stories + Rooftop ¦ 50 Residential Units
Aerial Precast Concrete Composite Deck System
PROJECT OVERVIEW
Building Type: | Mixed-use residential tower
Stories: | 7 stories + rooftop
Total Area: | 108,675 GSF
Structural System: | APC Filigree Composite Precast Deck
Construction Duration: | 18 months (vs 24 traditional)
Labor Reduction: | 30-40% vs traditional PT
APC FILIGREE SYSTEM BENEFITS
✓ Semi-precast system reduces on-site labor by 30-40%
✓ Eliminates traditional formwork and shoring
✓ Faster construction schedule (25% time savings)
✓ MEP conduits/pipes embedded between precast and topping slab
✓ 10% savings on electrical and plumbing (pre-laid before pour)
✓ Improved quality control (factory fabrication)
✓ Reduced concrete waste and material costs
✓ Integrated structural steel support system
✓ Fire-rated and code-compliant
✓ Suitable for high-rise construction
SCOPE OF WORK - APC FILIGREE SYSTEM
Item | Description | Quantity | Unit | Unit Price | Total | Notes
1 | APC Filigree Deck Panels | 108675 | SF | 28.5 |  | Factory fabricated
2 | Structural Steel Integration | 108675 | SF | 3.08 |  | Embedded supports
3 | MEP Conduit/Pipe Pre-Lay | 108675 | SF | 0.75 |  | Before topping pour
4 | Topping Concrete | 27168.75 | CY | 200 |  | 3" topping slab
5 | Panel Installation Labor | 108675 | SF | 2.5 |  | Crane & crew
6 | Shoring (minimal) | 21735 | SF | 1.5 |  | Temporary only
7 | Connections & Anchors | 350 | EA | 250 |  | Per floor connections
8 | Engineering & Shop Drawings | 1 | LS | 45000 |  | Structural PE
9 | Transportation & Delivery | 108.675 | Loads | 2500 |  | Per truck
10 | Crane Time | 90 | Days | 1200 |  | Tower crane rental
11 | Quality Control & Testing | 1 | LS | 25000 |  | Third party
SUBTOTAL
CONSTRUCTION SCHEDULE
Phase 1 | Shop Drawings & Fabrication |  |  | 2 months | Before on-site work
Phase 2 | Foundation & Columns |  |  | 3 months | Concurrent with fabrication
Phase 3 | Deck Installation (7 floors) |  |  | 9 months | 1.3 months per floor
Phase 4 | MEP & Finishes |  |  | 4 months | 25% overlap with structure
Total Duration | Ground to CO |  |  | 18 months | 6 months faster than traditional
SUBMITTAL REQUIREMENTS
1. Complete project pricing breakdown
2. Shop drawings and engineering calculations
3. Product data sheets and specifications
4. Quality control procedures
5. Installation schedule and sequence
6. Crane and equipment requirements
7. Testing and inspection protocols
8. Warranty information (minimum 2 years)
9. References from similar high-rise projects
10. Insurance certificates